## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | Estimate(hrs) | MOSCOW | Dependency | Assignee | Status
4 | 4 | US101 | Create Master Test Plan | 0.25 | MUST HAVE |  | Sumana Manna | 3-Done
4 | 4 | US102 | Prepare Product Backlog | 0.25 | MUST HAVE | US101 | Esha Kundu | 3-Done
4 | 4 | US103 | Prepare Sprint Backlog | 0.25 | MUST HAVE | US102 | Esha Kundu | 3-Done
4 | 4 | US104 | Design and set up Rest Assured framework | 0.5 | MUST HAVE | US103 | Shreetama Das | 3-Done
4 | 4 | US105 | Authenticate using login and retrieve access token | 0.5 | MUST HAVE | US104 | Shreetama Das | 3-Done
4 | 4 | US106 | Automate View Room List API | 0.5 | MUST HAVE | US105 | Sumana Manna | 3-Done
4 | 4 | US107 | Automate View Room By ID API | 0.5 | MUST HAVE | US105 | Sumana Manna | 3-Done
4 | 4 | US108 | Automate View Room By Type API | 0.5 | MUST HAVE | US105 | Esha Kundu | 3-Done
4 | 4 | US109 | Automate Add Room API | 0.5 | MUST HAVE | US105 | Esha Kundu | 3-Done
4 | 4 | US110 | Automate Update Room Price API | 0.5 | MUST HAVE | US105 | Shreetama Das | 3-Done
4 | 4 | US111 | Automate Delete Room By ID API | 0.5 | MUST HAVE | US105 | Shreetama Das | 3-Done
4 | 4 | US112 | Parameterize API tests using external JSON data | 0.5 | MUST HAVE | US104 | Esha Kundu | 3-Done
4 | 4 | US113 | Implement Negative Test Cases | 0.5 | MUST HAVE | US104, US105, US106, US107, US108, US109, US110, US111, US112 | Sumana Manna | 3-Done
4 | 4 | US114 | Generate Extent Report | 0.25 | MUST HAVE | US104, US105, US106, US107, US108, US109, US110, US111, US112 | Jyoti | 3-Done
4 | 4 | US115 | Test Execution Report | 0.25 | MUST HAVE | US104, US105, US106, US107, US108, US109, US110, US111, US112 | Jyoti | 3-Done
4 | 4 | US116 | Jira Deliverables | 0.25 | MUST HAVE | US104, US105, US106, US107, US108, US109, US110, US111, US112 | Jyoti | 3-Done