## Sheet1
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
[8 empty] | 6.5 | 0.75 | 0.5 | 0.5 | 1 | 1 | 2 | 0.75
SPRINT 4 BACKLOG
US101 | T001 | Create Master Test Plan | 2025-08-07 | 2025-08-07 | Sumana Manna | Design | 3- Completed | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
US102 | T002 | Prepare Product Backlog | 2025-08-07 | 2025-08-07 | Esha Kundu | Design | 3- Completed | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
US103 | T003 | Prepare Sprint Backlog | 2025-08-07 | 2025-08-07 | Esha Kundu | Design | 3- Completed | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
US104 | T004 | Design and set up Rest Assured framework | 2025-08-08 | 2025-08-08 | Shreetama Das | Build | 3- Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
US105 | T005 | Authenticate using login and retrieve access token | 2025-08-09 | 2025-08-09 | Shreetama Das | Coding | 3- Completed | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0
US106 | T006 | Automate View Room List API | 2025-08-10 | 2025-08-10 | Sumana Manna | Integration Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
US107 | T007 | Automate View Room By ID API | 2025-08-10 | 2025-08-10 | Sumana Manna | Integration Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0
US108 | T008 | Automate View Room By Type API | 2025-08-11 | 2025-08-11 | Esha Kundu | Integration Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
US109 | T009 | Automate Add Room API | 2025-08-11 | 2025-08-11 | Esha Kundu | Integration Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0
US110 | T010 | Automate Update Room Price API | 2025-08-12 | 2025-08-12 | Shreetama Das | Integration Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
US111 | T011 | Automate Delete Room By ID API | 2025-08-12 | 2025-08-12 | Shreetama Das | Integration Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
US112 | T012 | Parameterize API tests using external JSON data | 2025-08-12 | 2025-08-12 | Esha Kundu | Coding | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
US113 | T013 | Implement Negative Test Cases | 2025-08-12 | 2025-08-12 | Sumana Manna | Regression Test | 3- Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0
US114 | T014 | Generate Extent Report | 2025-08-13 | 2025-08-13 | Jyoti | System Test | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US115 | T015 | Test Execution Report | 2025-08-13 | 2025-08-13 | Jyoti | System Test | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
US116 | T016 | Jira Deliverables | 2025-08-13 | 2025-08-13 | Jyoti | Others | 3- Completed | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work